## Test Scenarios
Test ID | Category | Role / Persona | Scenario | Preconditions | Steps | Expected Result | Actual Result | Pass / Fail | Issue ID | Tester | Date Tested | Notes
TC-001 | Submission | Submitter | I can submit a new data breach report | Logged into the site hosting the form | Fill in all required fields and click Submit | Report is created; confirmation panel shows a reference number (e.g. DBN-123)
TC-002 | Submission | Submitter | I receive a confirmation email after submitting | Report just submitted | Check the submitter's inbox | Confirmation email received
TC-003 | Submission | Submitter | I can attach a file when submitting a report | On the submission form | Attach a file, complete the form, and submit | File appears as an attachment on the new report
TC-004 | Visibility | Submitter | I can see the request I submitted | Report submitted by this user | Open the report listing | Own report appears in the list with the correct reference
TC-005 | Visibility | Submitter | I cannot see requests I did not submit | Two reports exist, submitted by two different users | Log in as User A and browse the listing | Only reports User A submitted or is named on are visible; User B's unrelated report is absent
TC-006 | Visibility | Person Responsible | I can see a report I'm named as Person Responsible on, even though I didn't submit it | A report names User C as Person Responsible | Log in as User C and open the report | Report is visible and openable (read-only)
TC-007 | Visibility | Line Manager | I can see a report I'm named as Line Manager on | A report names User D as Line Manager | Log in as User D and open the report | Report is visible and openable (read-only)
TC-008 | Visibility | Unrelated user | I cannot see or open a report I have no relationship to | A report exists naming other individuals; tester is not named on it | Browse the listing, then try a direct link to the item | Report is absent from the listing; the direct link is denied
TC-009 | Editing | Submitter | I cannot edit my request after submitting | Report submitted by this user | Open own report and look for Edit controls on any section | No Edit option is shown; the report is read-only
TC-010 | Editing | Any user | I cannot edit other people's requests | Two reports exist, owned by different users | Log in as User A and attempt to reach User B's report edit controls directly | No edit controls are available / action is denied
TC-011 | Status | Submitter / Line Manager | I cannot change a report's status | Report is Open | Log in as submitter or line manager and open the report | No status controls are visible
TC-012 | Closure | Submitter | I cannot edit my request after it has been closed | Report status = Closed | Open own closed report | All sections remain read-only (same as before closing)
TC-013 | Closure | Submitter / Person Responsible / Line Manager | I lose access to a report once it's closed, if I'm only a named individual on it | Report status = Closed; tester is one of the named individuals on the report | Try to open the closed report | Access is denied
TC-014 | Communication | Person Responsible | I can submit more information when requested | Report status = needs more info; tester is the Person Responsible | Open the report and use the reply box | Reply is submitted and appended to the communication log
TC-015 | Communication | Submitter (not also Person Responsible) | I cannot see the "submit more information" reply action | Report status = needs more info; tester is submitter only | Open own report | No reply button is shown
TC-016 | Communication | Line Manager | I cannot see the reply action | Report status = needs more info | Open the report as Line Manager | No reply button is shown; communication history is still visible
TC-017 | Communication | Submitter | I can view the communication history on my report | Communication log has entries | Open own report | Communication log / history displays correctly
TC-018 | Reference | Any | The report reference number displays consistently everywhere | New or existing report | Check the listing, detail view, and any emails | The same reference number is shown consistently in every location

## Issue Log
Issue ID | Date Raised | Raised By | Related Test ID | Severity | Category | Description | Steps to Reproduce | Expected Result | Actual Result | Status | Assigned To | Date Resolved | Notes
ISS-001 |  |  | TC-013 | High | Closure | Example row — delete before use: named individual could still open a closed report. | 1. Close a report. 2. Log in as the report's Line Manager. 3. Open the report link. | Access denied once the report is closed. | Report opened successfully — access had not been removed. | Open

## Read Me
Data Breach Form — Test Plan & Issue Log
Test scenarios and issue tracking for the Data Breach Reporting form
Roles
Role | Definition
Submitter | The person who submitted the report.
Person Responsible | Named on the report as the person responsible for it. The only role that can reply with more information when it's requested.
Line Manager | Named on the report. Can view the report and its communication history, but cannot reply or edit anything.
Unrelated user | Anyone not named on the report at all. Should not be able to see or open it.
When to expect an email
Event | Who receives it
Report submitted | The submitter, the person responsible, and the line manager each get a confirmation email straight away.
More information requested | Only the person responsible gets an email asking them to reply.
You reply with more information | No confirmation email back to you — your reply is sent straight to the review team.
Report closed | The submitter, the person responsible, and the line manager each get a "case closed" email.
Note: if you hold more than one of these roles on the same report (e.g. you submitted it and are also the person responsible), you'll still only get one copy of each email, not one per role. Unrelated users don't receive any emails about a report they're not named on.